Strategic Plan

2015-2017

NASPA National Strategic Plan Goals

- Deliver dynamic, innovative, and timely professional development and volunteer engagement opportunities to build the leadership capacities and effectiveness of student affairs professionals

- Generate scholarship and disseminate knowledge that supports evidence-based, innovative, inclusive, and socially just student affairs practices

- Lead public policy and advocacy efforts that shape the changing landscape of student affairs within higher education

- Provide leadership for student affairs in integrating existing and emerging technologies

- Develop and promote NASPA’s identity as a global student affairs association

Goal #1:  Delivers dynamic, innovative, and timely professional development and volunteer engagement opportunities to build the leadership capacities and effectiveness of student affairs professionals.

| Action Item | Measurable Outcome | Milestones/ Completion Date | Individual(s) Responsible | Update |
| --- | --- | --- | --- | --- |
| #1 Create and implement a professional development series for seasoned mid-level professionals | Ten participants have been present at each of the programs offered during the first year | AY 15-16: Plan series AY 16-17: Implement series | Alison Black, Member-at-large | 11/16—Conducted survey in June ’16 of NASPA members to assess needs/interests of seasoned mid-level professionals. Results suggest creating a colleague network. Next step—launch an “MSL Colleague Network” (mid-senior level). Program session offered at regional conference. |
| #2A Establish a Membership Committee to welcome new members to the Region | A representative from each state and/or country has been identified | AY 15-16: Work with State/International Directors to identify individuals for Membership Committee & convene to review committee charge | Peter Fowler, Membership Coordinator State and International Directors, Regional Director-Elect | 11/16—Regional membership team has been established. Completed! |
| #2B Contact all new regional members via email and phone within two months of joining and provide them with direct assistance on how to complete their NASPA profiles | 85% of new members to the Region have been contacted, and their NASPA profiles have been updated | AY 16-17: Review NASPA central office communication calendar and develop regional strategies that enhance and integrate with central office plan | Peter Fowler, Membership Coordinator Committee established via Action Item 2A | 11/16—Outreach to new members from the membership team began in October 2016. This practice will be reviewed in Jan 2017 to determine effectiveness in new members updating their profile. Next step—conduct outreach, collect data and evaluate effectiveness. |
| #3 Create an online database where members can create a profile to become a mentor, and those individuals looking for mentors can search the database for professionals with particular experiences and with whom a direct mentoring connection could be made | 50 or greater mentor profiles established | AY 15-16: Planning & development AY 16-17: Implementation | Member-at-Large ? |  |
| #4 Provide one or more professional development opportunities within each of the states/provinces that are co-sponsored with another Region I entity or another professional association | Seven or more programs are held within the Region during the first year of implementation | TBD | Jennifer Maitino, Liaison to Professional Organizations |  |

Goal #2:  Generate scholarship and disseminate knowledge that supports evidence-based, innovative, inclusive, and socially just student affairs practices.

| Action Item | Measurable Outcome | Milestones/ Completion Date | Individual(s) Responsible | Update |
| --- | --- | --- | --- | --- |
| #5 Create wiki-style sites with basic explanations and proper use of the following: - Professional standards - Competencies - Research terminology | 50 or more views in first year; feedback survey with 85% satisfaction rate of site’s usefulness | AY 15-16: Planning & development AY 16-17: Implementation | Susan Marine, Faculty Council Representative Rozana Carducci, Professional Standards Representative Patricia Rissmeyer, Research Representative Brian Nangle, Technology Coordinator | 11/29/16 Update - Video Curriculum - The team agreed to create a video curriculum series. - Videos will be 10 minutes max and will include narrated slides, interviews with experts, and discussion questions. - Location: videos will be posted on a YouTube Channel (NASPA or a newly created Region I channel) and linked form a newly created resources page on the Region I website - Video Series Content: - Introduction to the ACPA/NASPA Professional Competencies (Carducci) - Purpose - Development process - Review of competencies, levels and points of emphasis - Examples of utilization - Resources - Starter discussion prompts - Introduction to the Competency Rubrics (Susan) - What is a rubric? - Review of dimensions, scale - Assessment methods and examples - Documentation of achievement - Examples of utilization - Resources - Starter discussion prompts - How you can use the competencies to plan intentional professional development - Self-assessment - Professional development opportunities - Campus - National - Create self-assessment tool as supplemental resource - NEASC Standards & Student Affairs (Rissmeyer) - Review of Standard 5 and relevance to Student Affairs - List of experts/resources - We decided to table this action item given concerns about maintaining the list. We will revisit at a later time. - Bibliography of sources: Develop a list of references related to competencies, standards, and rubrics. - Will compile in the spring - Post on Region I resources page and Professional Standards Division website Future goals: - Depending upon the success (utilization and feedback) of the video series, we will look to develop specific videos on each competency area. Action Steps: - Example of Storyboard (Carducci) - Storyboard/script for videos (January) - Practice conference call (zoom or got to meeting) (January) - Region I Facebook, blog, and Twitter soliciting examples of use and ideas for resources (January) - Production of videos (February/March ) - Post video series (March/April) Region I Leadership: Advocate for NASPA HQ to develop a web-based assessment and tracking tool for professional competencies / rubrics |
| #6 Create a research database that allows for collaboration on areas of research interests and interactions among faculty and practitioners | 50 or more views in first year; feedback survey with 85% satisfaction rate of site’s usefulness; number of collaborations TBD | AY 15-16: Planning & development AY 16-17: Implementation | Susan Marine, Faculty Council Representative Rozana Carducci, Professional Standards Representative Patricia Rissmeyer, Research Representative | 11/29/16 Update Explore with NASPA HQ the platform option possibilities (Nagle) |
| #7 Use the Regional Conference and social media (Ted Talk style/video segments/quick video clips) as a means of highlighting research (small or campus-based studies/dissertations/etc.) | Three or more research presentations in AY 16-17 | AY 15-16: Planning & development AY 16-17: Implementation | Susan Marine, Faculty Council Representative Rozana Carducci, Professional Standards Representative Patricia Rissmeyer, Research Representative Brian Nangle, Technology Coordinator | 11/29/16 Update Monthly series of video interviews with Region I scholars and published authors. - What platform will host series? - You Tube - How do we identify published research? - Facebook - Faculty email (Susan) - Solicit ideas for new PHDs - Format: 10 minute max - Dissemination - Add research tab to Region I webpage - Region I YouTube Channel Newsletter |

## Goal #3:  Lead public policy and advocacy efforts that shape the changing landscape of student affairs within higher education.

| Action Item | Measurable Outcome | Milestones/ Completion Date | Individual(s) Responsible | Update |
| --- | --- | --- | --- | --- |
| #8 Create a wiki-style site with basic explanations and proper use of public policy terms and/or key legislation | 50 or more views in first year; feedback survey with 85% satisfaction rate of site’s usefulness | AY 15-16: Planning & development AY 16-17: Implementation | Seann Kalagher, Public Policy Division Representative Brian Nangle, Technology Coordinator | 11/16—Action item on-hold as alternatives to “wiki-style” websites are considered. |
| #9 Develop a model for a “Day on the Hill” to meet with appropriate state legislators that can be duplicated by each of the states/provinces | Each state/province has had a “Day on the Hill” by the end of AY 18 | AY 15-16: Planning & development AY 16-17: Implementation | Seann Kalagher, Public Policy Division Representative State/International representatives | 11/16—Initial conference call in Oct ’16 with State coordinators to discuss creating a public policy infrastructure. |
| #10 Provide training for student affairs professional on dealing with the press and social media (optics) during and after a campus crisis (program can be a webinar, Ted Talk, etc.) | 5% of regional membership has been trained | AY 15-16: Planning & development AY 16-17: Implementation | Seann Kalagher, Public Policy Division Representative |  |

Goal #4:  Provide leadership for student affairs in integrating existing and emerging technologies.

| Action Item | Measurable Outcome | Milestones/ Completion Date | Individual(s) Responsible | Update |
| --- | --- | --- | --- | --- |
| #11 Create a “wiki-style” site with basic explanations of various technologies available to student affairs professionals | Measurable outcome: 50 or more views in first year; feedback survey with 85% satisfaction rate of site’s usefulness | AY 15-16: Planning & development AY 16-17: Implementation | Brian Nangle, Technology Coordinator | 11/16—Action item on-hold as alternatives to “wiki-style” websites are considered. |
| #12 Determine a list of emerging technologies and campus-based needs (i.e. disciplinary record keeping database) and invite three vendors to co-present with a student affairs professional on the topic area at the Regional Conference or drive-in workshop | Measurable outcome: 90% satisfaction rate of program presentation | AY 15-16: Planning & development AY 16-17: Implementation | Meghan Kenny, Regional Conference Chair | 11/16—Although this Action Item was communicated to conference chairperson after conference sessions/vendors were arranged, 5 sessions on emerging technologies and campus-based needs by corporate sponsors were offered at regional conference as well as 1 program session offered on technology jointly with a corporate entity. |

Goal #5:  Develop and promote NASPA’s identity as a global student affairs association.

| Action Item | Measurable Outcome | Milestones/ Completion Date | Individual(s) Responsible | Update |  |
| --- | --- | --- | --- | --- | --- |
| #13 Create a wiki-style site with basic explanations of various intercultural competencies that student affairs professionals should know | 50 or more views in first year; feedback survey with 85% satisfaction rate of site’s usefulness | AY 15-16: Planning & development AY 16-17: Implementation | Constance Cabello & Jen Stanley, KC Coordinators | 11/16—Action item on-hold as alternatives to “wiki-style” websites are considered. |  |
| #14 Every other year, select a NASPA Region I representative outside of the United States and provide financial support for attendance at the Regional Conference. In exchange, the selected individuals will provide two or three presentations about their work and student populations | 90% satisfaction rate of program presentation | AY 15-16: Planning & development AY 16-17: Implementation | Meghan Kenny, Regional Conference Chair Jenn Kosses, Treasurer | 11/16—Although this action item was set after conference planning had already occurred, the regional conference included attendees from Canada, the United Kingdom and Ireland, and at least 1 program session was offered by an international institutional member. |  |